**Edington Neighbourhood Plan**

Proposed plan of completion – draft

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | **Meeting group** | **Agenda** | **Notes** |
| November 2017 | Parish Council (PC) | Establish lead working group | This could be comprised of the chairs of the Local Development Plan (LDP) groups plus representatives from the Parish Council (Chair, Vice Chair, plus ???) |
| January 2018  Early July?? | Lead Working Group (LWG) | 1. Identify the visions and objectives for Edington 2. Identify neighbourhood area of remit for NP 3. Identify policy areas of concern to form the basis of the NP | The policy areas for concern can be based on the outcomes of the LDP plus other areas that the group feel are an integral part of the village.  NP area *(LDP area)*   * Built environment including housing, *(Amenities and facilities, housing)* * Countryside and nature, *(Environment including footpaths)* * Local economy and enterprise, *(Business and employment)* * Transport and infrastructure *(Highways, traffic and transport)* |
| April 2018  Early Nov?? | Annual Parish meeting (APM)  Village meeting | Present the initial work to the village | Neighbourhood area of remit and policy areas |
| May 2018 – March 2019 | LWG plus others | Produce the various sections of the plan | It is envisaged that the leads of the group will meet together at least bi-monthly to discuss progress and identify any areas of overlap/concern etc. |
| April 2019 | APM | Present update of NP | This will be followed by the open morning when villagers will be given the opportunity to come and view the plan in detail and make comments. (see below) |
| May – June 2019 | Open morning | Consultation with villagers on the proposals of the NP | 6 week consultation period |
| July 2019 | LWG | Complete the draft NP | This would include any amendments etc as a result of the consultation exercise |
| Late July 2019 – September 2019 | Wiltshire Council (WC) | Submit plan to Wiltshire Council | 6 week consultation plus admin time |
| October 2019 | WC | Plan submitted to independent examiner (IE) | 1 – 3 months? |
| January 2020 | LWG | Address any issues raised by IE | 1 month |
| March 2020 | WC | Community Referendum | Parish councils will not have to run the neighbourhood planning referendum – this will be the responsibility of Wiltshire Council. |
| April 2020 | APM | NP adopted by Wiltshire Council |  |